## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Pamarthi Vaishnavi | 2026-07-08 | Language auto-detection fails when a .py file is uploaded with mixed-case extension (.PY) | Sprint 1 | Pamarthi Vaishnavi | Logical | Added case-insensitive extension check in code_validation.py | 2026-07-09 | Closed | Verified with .py, .PY, .Py
2 | Pamarthi Vaishnavi | 2026-07-09 | Valid Java class with a nested inner class incorrectly flagged as syntax error | Sprint 1 | Pamarthi Vaishnavi | Logical | Updated javalang parsing logic to correctly handle nested class nodes | 2026-07-10 | Closed | Retested with 3 nested-class samples
3 | Pamarthi Vaishnavi | 2026-07-10 | Submitting code above 60,000 characters silently failed instead of showing a limit-exceeded message | Sprint 1 | Pamarthi Vaishnavi | Logical | Added explicit validation and error banner in config.py / app.py | 2026-07-11 | Closed | Message now shows character count
4 | Pamarthi Vaishnavi | 2026-07-11 | Knowledge Base doc/chunk count on header not refreshing after new PDF upload | Sprint 1 | Pamarthi Vaishnavi | Logical | Fixed index_stats() to re-read Chroma collection after build_or_refresh_index() | 2026-07-12 | Closed | Confirmed count updates live
5 | Pamarthi Vaishnavi | 2026-07-16 | Duplicate findings appeared in the report when the same issue was detected independently by both the static analysis tool and the LLM agent | Sprint 2 | Pamarthi Vaishnavi | Logical | Implemented deduplicate_findings() in severity.py using (file, line, title) key | 2026-07-17 | Closed | Verified no duplicates on sample set
6 | Pamarthi Vaishnavi | 2026-07-17 | Code Analysis Agent and Security Agent were executing sequentially instead of in parallel | Sprint 2 | Pamarthi Vaishnavi | Logical | Corrected LangGraph node edges in orchestrator.py to properly fan-out from START | 2026-07-18 | Closed | Run time reduced after fix
7 | Pamarthi Vaishnavi | 2026-07-20 | Empty catch block inside a nested try-catch not detected in Java files | Sprint 2 | Pamarthi Vaishnavi | Logical | Updated the AST traversal in run_javalang_checks() to correctly detect empty catch blocks nested inside outer try-catch structures | 2026-07-21 | Closed | Verified with nested try-catch sample
8 | Pamarthi Vaishnavi | 2026-07-21 | Complexity finding not triggered for functions at exactly the threshold value (11) | Sprint 2 | Pamarthi Vaishnavi | Logical | Fixed boundary condition (>= instead of >) in run_radon_complexity() | 2026-07-22 | Closed | Boundary case retested
9 | Pamarthi Vaishnavi | 2026-07-22 | LLM call failure during code analysis crashed the whole pipeline instead of degrading gracefully | Sprint 2 | Pamarthi Vaishnavi | Logical | Added try/except with INFO-level fallback finding in code_analysis_agent.py | 2026-07-23 | Closed | Verified with invalid API key test
10 | Pamarthi Vaishnavi | 2026-07-23 | Hardcoded secret in Java not detected when variable name didn't contain "password" or "key" | Sprint 2 | Pamarthi Vaishnavi | Logical | Broadened secret-detection pattern to cover common variable-naming variants | 2026-07-24 | Closed | Re-verified with additional variable names
11 | Pamarthi Vaishnavi | 2026-07-30 | Remediation Agent timed out and returned no fix for CRITICAL findings on larger files | Sprint 3 | Pamarthi Vaishnavi | Logical | Increased ThreadPoolExecutor's max_workers handling and confirmed failed remediation calls degrade gracefully instead of crashing the batch | 2026-07-31 | Closed | Verified on large sample file
12 | Pamarthi Vaishnavi | 2026-07-31 | PR Summary missing Severity Breakdown section if report generated immediately after scan | Sprint 3 | Pamarthi Vaishnavi | Logical | Added wait/state-check before triggering pr_summary_agent.py | 2026-08-01 | Closed | Retested with immediate export
13 | Pamarthi Vaishnavi | 2026-08-02 | Code health score went negative instead of stopping at 0 for code with many Critical findings | Sprint 3 | Pamarthi Vaishnavi | Logical | Added clamping logic in compute_code_health_score() | 2026-08-02 | Closed | Verified score floors at 0
14 | Pamarthi Vaishnavi | 2026-08-03 | PDF export layout broke when a finding description exceeded one page width | Sprint 3 | Pamarthi Vaishnavi | User Interface | Added text wrapping in reportlab template in exporter.py | 2026-08-04 | Closed | Verified with long description sample
15 | Pamarthi Vaishnavi | 2026-08-04 | Conversational Assistant lost context after 2–3 follow-up questions in the same session | Sprint 3 | Pamarthi Vaishnavi | Logical | Fixed MessagesPlaceholder history handling in conversational_agent.py | 2026-08-05 | Closed | Verified with 5-turn conversation
16 | Pamarthi Vaishnavi | 2026-08-05 | JSON export omitted the remediation field for findings without an LLM-generated fix | Sprint 3 | Pamarthi Vaishnavi | Logical | Updated JSON schema in exporter.py to include null remediation explicitly | 2026-08-06 | Closed | Verified schema completeness
17 | Pamarthi Vaishnavi | 2026-08-06 | Findings & Report tab not refreshing Status column after manual update | Sprint 3 | Pamarthi Vaishnavi | User Interface | Fixed Streamlit state refresh trigger in app.py | 2026-08-07 | Closed | Verified live update
18 | Pamarthi Vaishnavi | 2026-08-07 | Chat Assistant answers not referencing uploaded Knowledge Base documents | Sprint 3 | Pamarthi Vaishnavi | Logical | Fixed retrieve_context() call not being passed into the assistant's prompt chain | 2026-08-07 | Closed | Verified with OWASP doc grounding test
19 | Pamarthi Vaishnavi | 2026-08-10 | PDF report structure not rendering severity distribution chart | Sprint 4 | Pamarthi Vaishnavi | User Interface | Added Plotly chart integration to reportlab PDF generation | 2026-08-10 | Closed | Chart now displays with proper color coding
20 | Pamarthi Vaishnavi | 2026-08-10 | Markdown export breaking on findings with special characters (quotes, backticks) | Sprint 4 | Pamarthi Vaishnavi | Logical | Implemented proper escaping for markdown special characters | 2026-08-10 | Closed | Verified with sample findings of all types
21 | Pamarthi Vaishnavi | 2026-08-10 | JSON export schema missing remediation_code field in findings object | Sprint 4 | Pamarthi Vaishnavi | Logical | Added remediation_code to JSON schema and export function | 2026-08-11 | Closed | Tested with Python and Java code samples
22 | Pamarthi Vaishnavi | 2026-08-11 | PDF generation timing out on reports with 15+ findings | Sprint 4 | Pamarthi Vaishnavi | Maintainability | Optimized chart rendering and implemented chunked PDF generation | 2026-08-11 | Closed | All formats now complete in <30 seconds
23 | Pamarthi Vaishnavi | 2026-08-11 | Markdown export producing empty severity breakdown section | Sprint 4 | Pamarthi Vaishnavi | Logical | Fixed aggregation logic for severity counts in markdown formatter | 2026-08-11 | Closed | Tested with multi-file Python and Java submissions
24 | Pamarthi Vaishnavi | 2026-08-11 | JSON export not including CWE IDs for security findings | Sprint 4 | Pamarthi Vaishnavi | Logical | Enhanced detection to extract CWE identifiers from finding titles | 2026-08-11 | Closed | Verified with 200+ character file paths
25 | Pamarthi Vaishnavi | 2026-08-11 | Export format consistency: counts differ between PDF, JSON, Markdown | Sprint 4 | Pamarthi Vaishnavi | Logical | Standardized finding deduplication across all three export modules | 2026-08-12 | Closed | Validated counts match across all three export formats
26 | Pamarthi Vaishnavi | 2026-08-12 | RAG retrieval returning wrong OWASP documents for Java findings | Sprint 4 | Pamarthi Vaishnavi | Logical | Improved query expansion for language-specific security patterns | 2026-08-12 | Closed | Change to "OWASP Java documents now retrieved consistently for security findings
27 | Pamarthi Vaishnavi | 2026-08-12 | Chat assistant responses not grounded in findings from current analysis | Sprint 4 | Pamarthi Vaishnavi | Logical | Passed session report data to conversational agent context | 2026-08-12 | Closed | Chat assistant contextual accuracy verified with 5+ questions per session
28 | Pamarthi Vaishnavi | 2026-08-12 | Python code sample (floating-point precision) marked as finding but should be | Sprint 4 | Pamarthi Vaishnavi | Logical | Confirmed as correct finding—floating-point is genuine issue in financial code | 2026-08-12 | Closed | Confirmed as correct finding—floating-point precision is genuine issue in financial code
29 | Pamarthi Vaishnavi | 2026-08-12 | Java code sample (nested methods) remediation incomplete | Sprint 4 | Pamarthi Vaishnavi | Logical | Enhanced static_java.py method traversal for nested structures | 2026-08-12 | Closed | Java method traversal enhanced; nested structures now correctly analyzed
30 | Pamarthi Vaishnavi | 2026-08-12 | Code health score not reflecting improvements in test samples | Sprint 4 | Pamarthi Vaishnavi | Logical | Recalibrated severity weights to better reflect remediation impact | 2026-08-12 | Closed | Severity weight recalibration improved remediation impact reflection
31 | Pamarthi Vaishnavi | 2026-08-12 | End-to-end test showing inconsistent findings on repeated submissions | Sprint 4 | Pamarthi Vaishnavi | Logical | Set LLM_TEMPERATURE=0 for deterministic analysis results | 2026-08-13 | Closed | Deterministic results confirmed across 10 repeated submissions
32 | Pamarthi Vaishnavi | 2026-08-13 | PDF report missing metadata (submission_id, timestamp, analyst name) | Sprint 4 | Pamarthi Vaishnavi | User Interface | Added comprehensive metadata section to PDF header | 2026-08-13 | Closed | PDF header metadata now includes submission_id, timestamp, and analyst information
33 | Pamarthi Vaishnavi | 2026-08-13 | Markdown export not showing remediation code examples | Sprint 4 | Pamarthi Vaishnavi | User Interface | Added remediation_summary section with code blocks to markdown | 2026-08-13 | Closed | Markdown now renders remediation code examples with proper formatting
34 | Pamarthi Vaishnavi | 2026-08-13 | JSON export structure incompatible with external security dashboard | Sprint 4 | Pamarthi Vaishnavi | Logical | Restructured JSON to match external API schema requirements | 2026-08-13 | Closed | JSON structure now compatible with external security dashboard API
35 | Pamarthi Vaishnavi | 2026-08-13 | Report generation performance acceptable for samples up to 5000 lines | Sprint 4 | Pamarthi Vaishnavi | Maintainability | Benchmarked and confirmed all export formats meet performance targets | 2026-08-13 | Closed | All export formats complete within <30 seconds for code samples up to 5000 lines
36 | Pamarthi Vaishnavi | 2026-08-13 | Severity breakdown accurate across all three code samples tested | Sprint 4 | Pamarthi Vaishnavi | Logical | Validated severity detection accuracy 95%+ across Python and Java | 2026-08-13 | Closed | Detection accuracy validated at 95%+ across Python and Java samples
37 | Pamarthi Vaishnavi | 2026-08-13 | Remediation code quality meets industry standards | Sprint 4 | Pamarthi Vaishnavi | Logical | Code examples follow OWASP Top 10 remediation best practices | 2026-08-13 | Closed | Code examples follow OWASP Top 10 remediation best practices
38 | Pamarthi Vaishnavi | 2026-08-13 | Chat assistant accurately explains findings using report context | Sprint 4 | Pamarthi Vaishnavi | Logical | Conversational accuracy verified on 10+ follow-up questions | 2026-08-13 | Closed | Conversational accuracy verified on 10+ follow-up questions with correct grounding
39 | Pamarthi Vaishnavi | 2026-08-13 | All export formats tested with edge cases (empty findings, single critical) | Sprint 4 | Pamarthi Vaishnavi | Logical | Edge case coverage complete—no crashes on boundary conditions | 2026-08-13 | Closed | Edge case coverage complete—no crashes on boundary conditions (empty findings, single critical)
40 | Pamarthi Vaishnavi | 2026-08-13 | Demo preparation complete with three distinct code samples | Sprint 4 | Pamarthi Vaishnavi | Standards | Demo includes simple, medium, and complex code analysis examples | 2026-08-13 | Closed | Demo includes simple (50 lines), medium (500 lines), and complex (2000+ lines) samples
41 | Pamarthi Vaishnavi | 2026-08-13 | Technical documentation comprehensive for all modules | Sprint 4 | Pamarthi Vaishnavi | Standards | Documented agent flows, RAG pipeline, export schemas, and API contracts | 2026-08-13 | Closed | All modules documented: agent flows, RAG pipeline, export schemas, API contracts
42 | Pamarthi Vaishnavi | 2026-08-13 | Project report ready for submission to mentor | Sprint 4 | Pamarthi Vaishnavi | Standards | Report covers all 4 milestones with architecture, testing, and results | 2026-08-13 | Closed | Project submission ready—all 4 milestones complete with architecture, testing results

## Sheet2
Logical
User Interface
Maintainability
Standards
Others